## Sheet1
Task ID | Task Description | Reference | Assign to | Progress | Status | Comment
Basic
A1 | Requirement clarify |  | Maxwell | 100% | Complete | Constantly updating
A2 | UI Mockup |  | Sanji | 100% | Complete
A3 | Create Backend data structure |  | TEAM | 100% | Complete
A4 | prepare pre-data |  | TEAM | 100% | Complete
Create Request
General Information
B1 | Get information from backend |  | ERVIN | 50% | Inprogress | Perfect logical judgment
B2 | Pre-save information |  | ERVIN | 80% | Inprogress | Perfect logical judgment
Legal Entity
B3 | UI logic |  | ERVIN | 100% | Complete
B4 | Get information from backend |  | ERVIN | 50% | Inprogress
B5 | Embed "Exchange rate API" and use |  | ERVIN
B6 | Attachment store and get |  | ERVIN
B7 | Pre-save information |  | ERVIN | 80% | Inprogress | Perfect logical judgment
B9 | Save information to backend |  | ERVIN | 100% | Complete
B10 | Control display mode |  | ERVIN | 100% | Complete
Pre-assign
B11 | Get information from backend |  | ERVIN | 100% | Complete
B12 | Pre-save information |  | ERVIN | 80% | Inprogress | Perfect logical judgment
total
B13 | Save information to backend |  | ERVIN | 80% | Inprogress
B14 | Auto Generate No. |  | ERVIN | 100% | Complete
B16 | Save as Draft |  | ERVIN | 70% | Inprogress
Dashboard
C1 | Basic UI |  | TED | 100% | Complete
C2 | Get information from backend |  | TED | 80% | Inprogress
C3 | Tab banner control |  | TED | 100% | Complete
C4 | Filter function |  | TED | 100% | Complete
C5 | Search function |  | TED | 100% | Complete
C6 | Export function |  | TED
C7 | Navegation to request details |  | TED | 100% | Complete
C8 | paging control |  | TED
C9 | Button action (Delete/ resubmit/... ) |  | TED | 100% | Complete
C10 | Control display mode |  | TED | 100% | Complete
Review Request
Basic information
D1 | UI control |  | STONE | 50% | Inprogress
D2 | Get information from backend |  | STONE
Approval Workflow
D3 | UI control |  | STONE
D4 | Person card control |  | STONE
D5 | Comment box control |  | STONE
Total
D6 | UI control |  | STONE | 30% | Inprogress
D7 | Page navegation |  | STONE
D8 | Button action |  | STONE
Data migration
E1 | Create migration flow |  | DEE | 80% | Inprogress
E2 | Run the flow |  | DEE
Model driven app
F1 | Create model driven app |  | TED | 90% | Inprogress
Flow
G1 | Review Flow |  | STONE | 20% | Inprogress
G2 | Approval Flow |  | STONE | 20% | Inprogress
Actionable Email
H1 |  |  | STONE | 5% | Inprogress